## Slide 1: Quarterly Project Status Report, Q3 2026
Blue Defence · Programme Management Office · reported 6 October 2026
FICTIONAL SAMPLE DOCUMENT FOR WORKSHOP USE. Blue Defence and the content of this document are fictional.

## Slide 2: Project HALCYON: Sentinel-7 fleet expansion
Status: AMBER
8 of 12 vessels delivered
Cause: late delivery of battery modules from Volta Marine Energy
Recovery plan: remaining 4 vessels delivered by 15 December 2026
Budget SGD 18.6 million; SGD 11.2 million spent

## Slide 3: Project LANTERN: classified document search pilot
Status: GREEN
240 pilot users across 6 divisions
Go-live: 15 January 2027
Next step: accessibility testing in November 2026

## Slide 4: Project ORCHID: secure data centre migration
Status: RED
61 of 140 workloads migrated
12% over budget (SGD 1.4 million)
Decision needed: steering committee on 12 November 2026

## Slide 5: Portfolio summary
Project | Status | Key date
HALCYON | Amber | 15 December 2026: last 4 vessels
LANTERN | Green | 15 January 2027: go-live
ORCHID | Red | 12 November 2026: steering committee decision